## Sheet1
User_Story | Desc | Owner | Due_Date | Remarks | Type of Work
1 | Prepare a Business Model for our plan | Sid | 24( Tue end) | 22/11:Already have points. Need to draft that in a doc. This will include terms and conditions of registering on our website for both users and cateres | Non Technical
2 | Wireframes | Team | Work will go on for this | 22/11:Would be distributed acc to modules in seprate User Stories | Tech+Non Tech
3 | Registeration of our business | Armaan | 24th(Tue) | 22/11:Armaan will be discussing this with friends and then tell the approach. | Non Technical
4 | Domain | Sid/Team | End of this week | 22/11:We will have to think of a good name and then sid will be purchasing a domain corresponding to this. Need to complete this strictly in this week. | Non Technical
5 | DB | Sid/Team |  | 22/11:Will have to go with MYSQL for now. Will have to think for this for our next phase from performance point of view. | Technical
6 | Architecture of Proj | Armaan | End of this week | 22/11:Armaan will be deciding on which framework he will be using.Initially he has suggested to use spring.He will be fitting in all the designed components(till now) in the framework.Need to design tiles that will be consistent across pages.Can take view from BookMyParty and Zomato. | Technical
7 | Caterer Rgisteration Workflow | Tushar | 23rd(Mon) | 22/11: would be designing a.)wire frame for Caterer reg page+b.)Wireframe for this+c.)Complete flowchart(whole process should be clear) | Tech+Non Tech
8 | Customer View | Sid | 26(Thursday) | 22/11:Need to provide wireframe for this. Plus there should be complete and clear picture of what will be visible to user. | Tech+Non Tech
9 | Price Variablity Factor | Team | Start from next week | 22/11: This is an imp point. From today's discussion we concluded that we would be designing a page for caterers in which they can update price of all their dishes regularly( frequency yet to be decided). The caterer who would not be updating would be followed up by calling them. The caterers who still dont update their dish prices would be seen on screen with variablity factor calculated on basis of updation by other caterers for individual dishes. | Tech+Non Tech
10 | Prepare chroners | Bapu | Today | 22/11: Bapu to design chroners that will fetch data from bookmyparty website like reviews , ratings of cateres. | Tech
11 | Python to SQL | Bapu | Today | 22/11:Bapu to edit python script that fetches caterers from google API. It should directly insert data in MYSQL instead of preparing a CSV. | Technical
12 | Filters | Bapu | 25(Wed) | 22/11: Bapu to work on filters for website Includes :a.) Price/Budget b.)No of people c.)Date d.)Dishes Think more | Technical